## Sheet1
|  | Project Overview |  |  | Modules Overview
|  | Project Name | Timesheet Application |  | Module Name | Alloted Weightage | Completed Weightage | Start Date | Due Date | Completed Date
|  | Project Status | In-Process |  | Log-In | 20 | 14.2857 | 2018-06-11 | 2018-06-12
|  | Project Start Date | 2018-06-11 |  | Dashboard | 30 | 26.6667 | 2018-06-13 | 2018-06-28
|  | Project End Date | 2018-08-04 |  | Client | 50 | 21.4286
|  | Project Owner | Rinoy Babu
|  | Team | Bharat,Shani,Anas,Krushita,Garima,Shreya
|  | Technology Used | Dot Net with MVC
|  | Database | SQL |  | Total | 100 | 62.381
Modules | Task Details | Alloted Weightage | Owner | Start Date | Due Date | Status | Completed Weightage | Completed Date | Risk and Issues | Comments
LOGIN
| Project Initiation | 2.8571 |  | 2018-06-11 | 2018-06-11 | Completed | 2.8571 | 2018-06-11
| Username | 2.8571 | Krushita | 2018-06-11 | 2018-06-11 | Completed | 2.8571 | 2018-06-11
| Password | 2.8571 | Krushita | 2018-06-11 | 2018-06-11 | Completed | 2.8571 | 2018-06-11
| Client Mapping | 2.8571 | Garima,Shreya | 2018-06-11 | 2018-06-11 | Completed | 2.8571 | 2018-06-11
| Forgot Password | 2.8571 | Anas,Shani | 2018-06-12 | 2018-06-12 | Pending | 0 |  | firewall issue
| Remember me | 2.8571 | Krushita | 2018-06-12 | 2018-06-12 | Completed | 2.8571 | 2018-06-12
| CSS work | 2.8571 | Krushita | 2018-06-12 | 2018-06-12 | Pending | 0
DASHBOARD
| Country/Client Dropdown | 3.3333 | Krushita | 2018-06-13 | 2018-06-13 | Completed | 3.3333 | 2018-06-13 |  | dropdowns (Country name,Client id)
| Country/Client Mapping | 3.3333 | Garima,Shreya | 2018-08-14 | 2018-08-15 | Completed | 3.3333 | 2018-08-15 |  | client mapping
| Date Filter | 3.3333 | Krushita | 2018-08-15 | 2018-08-15 | Completed | 3.3333 | 2018-08-15
| Pie Chart-1 (front end) | 3.3333 | Anas,shreya | 2018-06-18 | 2018-06-19 | Completed | 3.3333 | 2018-06-19
| Pie Chart-1 (Back end) | 3.3333 | Garima,Shreya | 2018-06-18 | 2018-06-19 | Completed | 3.3333 | 2018-06-19
| User Client Mapping | 3.3333 | Garima,Shreya | 2018-06-19 | 2018-06-20 | Completed | 3.3333 | 2018-06-20
| CSS work | 3.3333 | Krushita | 2018-06-21 | 2018-06-22 | In Process | 0
| Bar Chart -(front end) | 3.3333 | Anas,Shreya | 2018-06-25 | 2018-06-26 | Completed | 3.3333 | 2018-06-29
| Bar Chart -(Back end) | 3.3333 | Anas,Shreya | 2018-06-27 | 2018-06-28 | Completed | 3.3333 | 2018-06-29
CLIENT
| Country/Client Dropdown | 7.1429 | Krushita | 2018-06-29 | 2018-06-29 | Completed | 7.1429 | 2018-06-28
| Country/Client Mapping | 7.1429 | Garima,Shreya | 2018-07-02 | 2018-07-03 | Completed | 7.1429 | 2018-06-28
| Date Filter | 7.1429 | Krushita | 2018-06-29 | 2018-06-29 | Completed | 7.1429 | 2018-06-28
| Pie Chart-2 | 7.1429 | Anas | 2018-07-04 | 2018-07-06 | Yet to Start | 0
| Grid View | 7.1429 | Shani | 2018-07-09 | 2018-07-13 | Yet to Start | 0
| View details-Grid view | 7.1429 | Shani | 2018-07-09 | 2018-07-13 | Yet to Start | 0
| Send Mail-Grid view | 7.1429 | Shani | 2018-07-09 | 2018-07-13 | Yet to Start | 0
| Total | 100 |  | 2018-06-11 | 2018-08-04 | In-Process | 62.381